## TestCases
Project: 2022-2023-project-4-game-design-Team-3
| Priority Levels | Colors
High
Medium
Low
Test case (25 items) | [6 empty] | Test Run | Thomas Planchard |  |  |  | Test Run 2 | Thomas Planchard |  |  |  | Test Run 3 | Thomas Planchard |  |  |  | Test Run 4 | Thomas Planchard |  |  |  | Test Run 5 | Thomas Planchard |  |  |  | Test Run 6 | Thomas Planchard
ID | Function | Priority | Description | Inputs | Expected Results | Status | Result | Date | Comments | Version | OS | Result | Date | Comments | Version | OS | Result | Date | Comments | Version | OS | Result | Date | Comments | Version | OS | Result | Date | Comments | Version | OS | Result | Date | Comments | Version | OS
1 | Movement | High | Test basic movement controls | Arrow keys / QD | The player moves right and left as expected when the key is pressed with a complete animation. | Pass | Kazuo moves when the player presses the arrow keys. However, it was observed that the QD input does not work as intended. While the "D" key works properly to move Kazuo right, pressing the "Q" key triggers an animation of attack instead of moving Kazuo left. | 2023-03-06 | Another issue that was observed during testing is related to Kazuo's running animation. Specifically, it was noticed that the animation is not fluid and appears jerky. | 0.1 | MACOS, Ventura 13.2.1 | Kazuo moves when the player presses the arrow keys. However, it was observed that the QD input does not work as intended. While the "D" key works properly to move the Kazuo right, pressing the "Q" key do nothing instead of moving the Kazuo left. | 2023-03-09 | Kazuo's running animation still not fluid and appears jerky. | 0.2 | MACOS, Ventura 13.2.1 | Kazuo moves when the player presses the arrow keys. However, it was observed that the QD input does not work as intended. While the "D" key works properly to move the Kazuo right, pressing the "Q" key trigger a parade animation instead of moving the Kazuo left. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Kazuo moves when the player presses the arrow keys. However, it was observed that the QD input does not work as intended. While the "D" key works properly to move the Kazuo right, pressing the "Q" key do nothing instead of moving the Kazuo left. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | Kazuo moves when the player presses the arrow keys and "Q" and "D". | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | Kazuo moves when the player presses the arrow keys and "Q" and "D". | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
2 | Dodge | High | Test dodging controls | Shift key | Player performs dodge as intended | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Kazuo dodges as intended when the player press the shift key + Left/right | 2023-03-13 | Currently Kazuo with the dodge can jump over the whole map and this broke the core of the game and its difficulty. | 0.4 | MACOS, Ventura 13.2.1 | Kazuo dodges as intended when the player press the shift key + Left/right | 2023-03-14 | The size of the dodge is again a little bit to strong compare to the difficulty of the game that we want. | 0.5 | MACOS, Ventura 13.2.1 | Kazuo dodges as intended when the player press the shift key + Left/right | 2023-03-21 | The team recommends adjusting the dash move to improve the gameplay experience. The dash move in the game is too long, making it difficult for the player to control the character. | 0.7 | MACOS, Ventura 13.2.1
3 | Jump | High | Test Jump | Space bar | The player is able to jump with a complete animation | Pass | Kazuo jump when the player press the space bar. | 2023-03-06 | The animation is not as intended. | 0.1 | MACOS, Ventura 13.2.1 | Kazuo jump when the player press the space bar. | 2023-03-09 | The animation is not as intended. | 0.2 | MACOS, Ventura 13.2.1 | Kazuo jump when the player press the space bar. | 2023-03-11 | The animation is not as intended. | 0.3 | MACOS, Ventura 13.2.1 | Kazuo jump when the player press the space bar. | 2023-03-13 | The animation is not as intended. | 0.4 | MACOS, Ventura 13.2.1 | Kazuo jump when the player press the space bar. | 2023-03-14 | The animation is not as intended. | 0.5 | MACOS, Ventura 13.2.1 | Kazuo jump when the player press the space bar. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
4 | Attack | High | Test attacking controls | A key | Player performs attack combo as intended. The player must press the "A" key to make an attack and when he presses it twice, he makes two different attacks. | In Progress | Kazuo can perform two different attacks, it was observed that they cannot be executed by clicking "A" key, but rather by pressing the "AZE" keys. Additionally, it was noticed that these attacks do not inflict any damage on enemies. | 2023-03-06 | It appears that the animations associated with each attack may be broken, as only the starting animation for each attack is visible. | 0.1 | MACOS, Ventura 13.2.1 | Kazuo can perform two different attacks, it was observed that they cannot be executed by pressing the "A" key, but rather by pressing the "AZ" keys. | 2023-03-09 | It seems that the animations associated with each attack are running as expected. However, a stamina bar is visible and should not be there. The player should be able to spam Kazuo's attacks. | 0.2 | MACOS, Ventura 13.2.1 | Kazuo can perform two different attacks, it was observed that they cannot be executed by pressing the "A" key, but rather by pressing the "AZ" keys. | 2023-03-11 | It seems that the animations associated with each attack are running as expected. One area for improvement is the hitbox for these attacks. We have to be too close to the enemy to kill them. Moreover sometime you are able to kill an enemy without animation of attack. | 0.3 | MACOS, Ventura 13.2.1 | The player can perform two different attacks by pressing the "A" key. The player must press twice very quickly to trigger the animation of the second attack. | 2023-03-13 | It seems that the animations associated with each attack are running as expected. One area for improvement is the hitbox for these attacks. We have to be too close to the enemy to kill them. Moreover sometime you are able to kill an enemy without animation of attack. | 0.4 | MACOS, Ventura 13.2.1 | The player can perform two different attacks by pressing the "A" key. The player must press twice very quickly to trigger the animation of the second attack. | 2023-03-14 | It seems that the animations associated with each attack are running as expected. One area for improvement is the hitbox for these attacks. We have to be too close to the enemy to kill them. Moreover sometime you are able to damage an enemy without animation of attack. | 0.5 | MACOS, Ventura 13.2.1 | The player can perform two different attacks by pressing the "A" key. The player must press twice very quickly to trigger the animation of the second attack. | 2023-03-21 | One area for improvement is the hitbox for these attacks. We have to be too close to the enemy to kill them. Moreover sometime you are able to damage an enemy without animation of attack. Finally we can spam attack in the air and be able to fly | 0.7 | MACOS, Ventura 13.2.1
5 | Kazuo life | High | Test if Kazuo dies from a blow from any enemy | Take a hit from all the enemies | Kazuo should die from a blow of any enemy | Pass | Kazuo take more than one hit to die. | 2023-03-06 | none | 0.1 | MACOS, Ventura 13.2.1 | Kazuo take more than one hit to die. | 2023-03-09 | Kazuo should not be have a health bar. (cf. Functional specification) | 0.2 | MACOS, Ventura 13.2.1 | Kazuo take one hit to die. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Kazuo take one hit to die. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | Kazuo take one hit to die. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | Kazuo take one hit to die. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
6 | Rank 1: enemy life | High | Test if the enemy 1 dies from a blow from the Kazuo | Take a hit from all the enemies | Enemy 1 should die from a blow of Kazuo | Pass | Kazuo need to hit more than one time to kill a enemy rank 1. | 2023-03-06 | none | 0.1 | MACOS, Ventura 13.2.1 | Kazuo need to hit one time to kill a enemy rank 1. | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Kazuo need to hit one time to kill a enemy rank 1. | 2023-03-11 | When an enemy is killed in the air the body still in the air and doesn't fall to the ground | 0.3 | MACOS, Ventura 13.2.1 | Kazuo need to hit one time to kill a enemy rank 1. | 2023-03-13 | When an enemy is killed in the air the body still in the air and doesn't fall to the ground | 0.4 | MACOS, Ventura 13.2.1 | Kazuo need to hit one time to kill a enemy rank 1. | 2023-03-14 | When an enemy is killed in the air the body still in the air and doesn't fall to the ground | 0.5 | MACOS, Ventura 13.2.1 | Kazuo need to hit one time to kill a enemy rank 1. | 2023-03-21 | When an enemy is killed in the air the body still in the air and doesn't fall to the ground | 0.7 | MACOS, Ventura 13.2.1
7 | Rank 2: enemy life | High | Test if the Kazuo dies from a blow from any enemy | Take a hit from all the enemies | Enemy 2 should die from 2 blow of Kazuo | Pass | Not implemented | 2023-03-06 | none | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Kazuo need to hit two time to kill a enemy rank 2. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | Kazuo need to hit two time to kill a enemy rank 2. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | Kazuo need to hit two time to kill a enemy rank 2. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
8 | Rank 1: enemy | High | Test the enemy rank 1 behavior | Getting close to the enemy | enemy should follow Kazuo and try to kill him | In Progress | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-06 | The animation of his attack is to close to Kazuo. The knife goes through Kazuo's body. Moreover, when the enemy runs, his feet do not touch the ground. | 0.1 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-09 | Cf. Test Run 1 | 0.2 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-11 | The animation of his attack is to close to Kazuo. The knife goes through Kazuo's body. | 0.3 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-13 | The animation of his attack is to close to Kazuo. The knife goes through Kazuo's body. | 0.4 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-14 | The animation of his attack is to close to Kazuo. The knife goes through Kazuo's body. | 0.5 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-21 | The animation of his attack is to close to Kazuo. The knife goes through Kazuo's body. | 0.7 | MACOS, Ventura 13.2.1
9 | Rank 2: enemy | High | Test the enemy rank 2 behavior | Getting close to the enemy | enemy should follow Kazuo and try to kill him | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. | 2023-03-13 | His attack animation is too slow. The player can easily dodge his attacks. | 0.4 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. Moreover, this enemy is able to stop and follow Kazuo in order to be unpredictable | 2023-03-14 | His attack animation is too slow. The player can easily dodge his attacks. | 0.5 | MACOS, Ventura 13.2.1 | The enemy correctly follows and attacks Kazuo as he enters the enemy's trigger zone. Moreover, this enemy is able to stop and follow Kazuo in order to be unpredictable | 2023-03-21 | His attack animation is too slow. The player can easily dodge his attacks. | 0.7 | MACOS, Ventura 13.2.1
10 | Boss Fight | High | Test boss fight mechanics | Interact with boss Kazuo | Boss behaves as intended, challenging the player to defeat it | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | There is only the first boss implemented. This boss has so far the same behaviour as a regular enemy. Moreover, his health bar is too short and he dies after two hits from Kazuo. | 2023-03-14 | For visibility, it is best to place the fixed health bar at the top centre of the screen. | 0.5 | MACOS, Ventura 13.2.1 | All the bosses are currently implemented in the game. However, the first and second bosses behave the same as regular enemies, which is not the intended behavior. This can make the boss fights less exciting and reduce the challenge level for players. On the other hand, the final boss's flying behavior is cool and adds to the overall experience. | 2023-03-21 | The team recommends adjusting the first and second bosses' behavior to make them more unique and challenging, which can enhance the overall boss fight experience. | 0.7 | MACOS, Ventura 13.2.1
11 | Collision | High | Test collision detection | Move player through obstacles | Player is blocked by obstacles as intended | Pass | It was observed that Kazuo is able to collide with the floor. But it was noticed that Kazuo falls into the void when reaching the limit of the map. | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with the floor. But it was noticed that Kazuo falls into the void when reaching the limit of the map. | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with the floor. But it was noticed that Kazuo falls into the void when reaching the limit of the map. | 2023-03-11 | Kazuo does not die when he falls into the void when he should die. | 0.3 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with the floor. But it was noticed that Kazuo falls into the void when reaching the limit of the map. | 2023-03-13 | Kazuo does not die when he falls into the void when he should die. | 0.4 | MACOS, Ventura 13.2.1 | It has been observed that Kazuo is able to collide with the floors and walls of different levels. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | It has been observed that Kazuo is able to collide with the floors and walls of different levels. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
12 | Collision with enemy rank 1 | High | Test collision detection with enemy 1 | Move player through enemy 1 | Player is blocked by the enemy 1 as intended | In Progress | It was observed that Kazuo is able to collide with enemy 1. | 2023-03-06 | When the player collides with an enemy, the enemy is too close to the player and its animation passes through the player. | 0.1 | MACOS, Ventura 13.2.1 | It was observed that the Kazuo is able to collide with enemy 1 | 2023-03-09 | When the player collides with an enemy, the enemy is too close to the player and its animation passes through the player. | 0.2 | MACOS, Ventura 13.2.1 | It was observed that the Kazuo is able to collide with enemy 1 | 2023-03-11 | When the player collides with an enemy 1, the enemy is too close to the player and its animation passes through the player. | 0.3 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with enemy 1 | 2023-03-13 | When the player collides with an enemy 1 the enemy is too close to the player and its animation passes through the player. | 0.4 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with enemy 1 | 2023-03-14 | When Kazuo collides with an enemy, he should be able to be pushed away by the enemy to prevent the animations from passing through the different characters. Also Kazuo should not be able to bounce infinitely on an enemy without being killed. | 0.5 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with enemy 1 | 2023-03-21 | When Kazuo collides with an enemy, he should be able to be pushed away by the enemy to prevent the animations from passing through the different characters. Also Kazuo should not be able to bounce infinitely on an enemy without being killed. | 0.7 | MACOS, Ventura 13.2.1
13 | Collision with enemy rank 2 | High | Test collision detection with enemy 2 | Move player through enemy 2 | Player is blocked by the enemy 2 as intended | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with enemy 2 | 2023-03-13 | When the player collides with an enemy 2, the enemy is too close to the player and its animation passes through the player. | 0.4 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with enemy 1 | 2023-03-14 | Same as Collision with enemy rank 1 | 0.5 | MACOS, Ventura 13.2.1 | It was observed that Kazuo is able to collide with enemy 1 | 2023-03-21 | Same as Collision with enemy rank 1 | 0.7 | MACOS, Ventura 13.2.1
14 | Collision with Bosses | High | Test collision detection with all the bosses | Move player through the different bosses | Player is blocked by the different bosses as intended | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | Currently, only the first boss is implemented. This boss has the same collision characteristics as a normal enemy. Kazuo collides directly with it left and right, but if you jump on it, it can bounce back endlessly. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | We found an issue related to the collision of the first and second bosses. It appears that the collision with these bosses is not working as expected, making it difficult for players to engage in combat. However, the final boss's collision is working well. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
15 | Audio | Medium | Test audio | Play game audio and sound effects | Audio plays and sound effects work as intended | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | The music in the main menu is quite good and matches the atmosphere of the game | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The music in the main menu is quite good and matches the atmosphere of the game | 2023-03-13 | No music in the game | 0.4 | MACOS, Ventura 13.2.1 | The music in the main menu is quite good and matches the atmosphere of the game | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | The music in the main menu is quite good and matches the atmosphere of the game | 2023-03-21 | Two buttons were expected for music and sound settings, but it appears that this feature is missing. The testing team recommends adding separate buttons for music and sound settings | 0.7 | MACOS, Ventura 13.2.1
16 | Performance | Medium | Test game performance on different computer systems | Run game on different computer systems | Game runs smoothly and meets minimum performance requirements | Pass | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | The game was tested with Google Chrome, Discord, Slack, Epic Games, Visual Studio opened and the game run without lag. | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | The game was tested with Google Chrome, Discord, Slack, Epic Games, Visual Studio opened and the game still run without lag. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The game was tested with Google Chrome, Discord, Slack, Epic Games, Visual Studio opened and the game still run without lag. Same result on mac and widows | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2 | The game has been tested with Google Chrome, Discord, Slack, Epic Games, Visual Studio open and the game still runs without lag. Furthermore, the game was tested with an open activity monitor and it showed that Slack or Discord take 1.5 more memory than our game. | 2023-03-14 | After 10 minutes of open play, the Macos starts to overheat slightly. | 0.5 | MACOS, Ventura 13.2.1,Windows 11 Pro 21H2 | The game has been tested with Google Chrome, Discord, Slack, Epic Games, Visual Studio open and the game still runs without lag. Furthermore, the game was tested with an open activity monitor and it showed that Slack or Discord take 1.5 more memory than our game. | 2023-03-21 | After 10 minutes of open play, the Macos starts to overheat slightly. | 0.7 | MACOS, Ventura 13.2.1,Windows 11 Pro 21H2
17 | Compatibility | Medium | Test game compatibility on different OS versions | Run game on different OS versions | Game runs without issues on different OS versions | Pass | The game was run on two different operating systems and no issues were observed. The game ran correctly on both Windows and Mac OS platforms. | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2 | The game was run on two different operating systems and no issues were observed. The game ran correctly on both Windows and Mac OS platforms. | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2 | The game was run on two different operating systems and no issues were observed. The game ran correctly on both Windows and Mac OS platforms. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2 | The game was run on two different operating systems and no issues were observed. The game ran correctly on both Windows and Mac OS platforms. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2 | The game was run on two different operating systems and no issues were observed. The game ran correctly on both Windows and Mac OS platforms. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2 | The game was run on two different operating systems and no issues were observed. The game ran correctly on both Windows and Mac OS platforms. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1, Windows 11 Pro 21H2
18 | Tutorial | Low | Test tutorial system | Complete tutorial steps | Player understands how to play the game as intended | FAIL | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Missing tutorial. When you start the game, the text in the right corner of the screen is outdated and does not correspond to the right inputs of the game. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | Missing tutorial. When you start the game, the text in the right corner of the screen is outdated and does not correspond to the right inputs of the game. | 2023-03-14 | The place where the game instructions are written with the inputs is editable, so that if the player wants to, he can erase everything. It should be impossible to do this | 0.5 | MACOS, Ventura 13.2.1 | Missing tutorial. When you start the game, the text in the right corner of the screen is outdated and does not correspond to the right inputs of the game. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
19 | Accessibility | Low | Test font size and contrast | Adjust font size and contrast settings | Text is readable for players with visual impairments as intended | FAIL | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The colours of the buttons in the user interface are not the best choice, they do not fit well with the theme of the game. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | The colours of the buttons in the user interface are not the best choice, they do not fit well with the theme of the game. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | It appears that the font used is not legible, which could hinder the player's ability to read the instructions and game text. It seems that there is a problem with the designer of the game's buttons. Finally the testing team found an issue related to the colors used in the game, which can affect the player's immersion. | 2023-03-21 | It is recommended that a more legible font be used to improve user experience and also we recommends having the game's buttons redesigned to improve the game's user interface. | 0.7 | MACOS, Ventura 13.2.1
20 | Double Jump | High | Test double jump function | Press jump button twice in quick succession | Player performs double jump as intended | Pass | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | When the player presses the space bar twice, Kazuo jumps twice in a row. | 2023-03-11 | The size of your double jump depends on the speed of your click. | 0.3 | MACOS, Ventura 13.2.1 | When the player presses the space bar twice, Kazuo jumps twice in a row. | 2023-03-13 | The size of your double jump depends on the speed of your click. | 0.4 | MACOS, Ventura 13.2.1 | When the player presses the space bar twice, Kazuo jumps twice in a row. | 2023-03-14 | The size of your double jump depends on the speed of your click. | 0.5 | MACOS, Ventura 13.2.1 | When the player presses the space bar twice, Kazuo jumps twice in a row. | 2023-03-21 | The size of your double jump depends on the speed of your click. | 0.7 | MACOS, Ventura 13.2.1
21 | Boss Difficulty | High | Test boss difficulty level | Fight multiple bosses throughout the game | Bosses become progressively more challenging as the player progresses, with a final boss that is appropriately difficult for the end of the game | FAIL | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | Currently, only the first boss is implemented. This boss has a very low difficulty and can be beaten in 2 moves. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | All the bosses are currently implemented in the game, but their difficulty level is not as intended. The bosses' difficulty levels are lower than expected, which can make the game too easy for players. | 2023-03-21 | The team recommends adjusting the difficulty levels of the bosses to provide a more challenging gameplay experience. | 0.7 | MACOS, Ventura 13.2.1
22 | Time limit | High | Test the time limit of the game | Play game until 10min | There will be a limit of 10 minutes for the player to finish the whole game | Pass | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The time limit of the game is not 10min as intended. Positive point Kazuo is killed after the end of the timer | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | The time limit of the game is not 10min as intended. Positive point Kazuo is killed after the end of the timer | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | The time limit of the game is 10min as intended and Kazuo is killed after the end of the timer | 2023-03-21 | . It appears that the game does not show the player's best time in the corner of the screen. The team recommends adding this feature to improve the user experience. | 0.7 | MACOS, Ventura 13.2.1
23 | Visuals | High | Test visual quality | Play game at different resolutions and graphics settings | Graphics are of high quality, with no glitches or visual artifacts present | FAIL | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | At the moment, players cannot choose their own resolution to play the game. | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | In each level, when you make the first animation of each move, a brown spot appears on Kazuo for 0.5 seconds. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | In each level, when you make the first animation of each move, a brown spot appears on Kazuo for 0.5 seconds. In addition, the background of the first level is not complete and leaves a black background | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | In each level, when you make the first animation of each move, a brown spot appears on Kazuo for 0.5 seconds. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | In each level, when you make the first animation of each move, a brown spot appears on Kazuo for 0.5 seconds. | 2023-03-21 | The team recommends adjusting the sprite speed to improve the gameplay experience. | 0.7 | MACOS, Ventura 13.2.1
24 | Input Lag | Medium | Test input lag and responsiveness | Play game with keyboard and mouse or gamepad | Inputs are responsive with minimal lag, allowing the player to perform actions as intended without any noticeable delay | Pass | The responsiveness of the game's inputs was evaluated. It was observed that there is a minimal lag time between pressing a key and Kazuo's response. The lag time was within acceptable limits and did not have a significant impact on gameplay. | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | The lag time was within acceptable limits and did not have a significant impact on gameplay. | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | The lag time was within acceptable limits and did not have a significant impact on gameplay. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The lag time was within acceptable limits and did not have a significant impact on gameplay. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | The lag time was within acceptable limits and did not have a significant impact on gameplay. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | The lag time was within acceptable limits and did not have a significant impact on gameplay. | 2023-03-21 | None | 0.7 | MACOS, Ventura 13.2.1
25 | User Interface | Low | Test user interface and menus | Navigate through game menus and pause menu | Menus and pause menu are intuitive and easy to navigate, providing the necessary information to the player in a clear and concise manner | In Progress | Not implemented | 2023-03-06 | None | 0.1 | MACOS, Ventura 13.2.1 | Not implemented | 2023-03-09 | None | 0.2 | MACOS, Ventura 13.2.1 | The main menu is composed of 3 buttons (New game, settings, quit game) New game and quit game work fine but the settings button does not work. Also, when we press escape in the game, a menu appears with the same 3 buttons and the same problem appears. | 2023-03-11 | None | 0.3 | MACOS, Ventura 13.2.1 | The main menu is composed of 3 buttons (New game, settings, quit game) New game and quit game work fine but the settings button does not work. Also, when we press escape in the game, a menu appears with the same 3 buttons and the same problem appears. | 2023-03-13 | None | 0.4 | MACOS, Ventura 13.2.1 | The main menu is composed of 3 buttons (New game, settings, quit game) New game and quit game work fine but the settings button does not work. Also, when we press escape in the game, a menu appears with the same 3 buttons and the same problem appears. | 2023-03-14 | None | 0.5 | MACOS, Ventura 13.2.1 | Two buttons were expected for music and sound settings, but it appears that this feature is missing. It seems that there is a problem with the designer of the game's buttons. | 2023-03-21 | The testing team recommends adding separate buttons for music and sound settings to enhance user experience. The testing team recommends having the game's buttons redesigned to improve the game's user interface. | 0.7 | MACOS, Ventura 13.2.1

## Graphics
Passed: | 11 | Version | Date | Passed | Remaining Tests
Failed: | 4
In progress: | 10 | 0.0 | 2023-03-04 | 0% | 100%
Not Implemented | 0 | 0.1 | 2023-03-06 | 8% | 92%
Result: | Fail | 0.2 | 2023-03-09 | 16% | 84%
|  | 0.3 | 2023-03-11 | 24% | 76%
|  | 0.4 | 2023-03-13 | 28% | 72%
|  | 0.5 | 2023-03-14 | 40% | 60%
|  | 0.7 | 2023-03-21 | 44% | 56%

## DataList(not to be opened) (hidden)
Thomas Planchard | FAIL
Karine Vinette | In Progress
Lucas Aubard | Pass
Paul Nowak | Not Implemented
100%
90%
80%
70%
60%
50%
40%
30%
20%
10%
0%

## Result Test Session 10032023 (hidden)
Horodateur | What is your overall impression of the game ? | How would you rate the game's graphics and visual effects? | How responsive were the game controls? Were there any issues with latency or delay? | How difficult was the game? Did you find it too easy, too difficult, or just right? | Were there any bugs, glitches, or technical issues that you encountered while playing? | Would you recommend this game to others? | Is there anything else you'd like to share about your experience playing the game? | How would you rate the game's controls ? | Do you like that we can be kill by one hit ? | Do you fin the game fluid and smooth ?
2023-03-10 14:53 | Good. Very promising, needs a level design concept, but its a pretty polished prototype. | 8 | Quite responsive. The double jump is well done, but the movement feels sluggish at times. | 2 | Nothing beyond the obvious. | 3 | Looking forward to seeing a more evolved version. A bit of extra works on the mechanics and more interesting levele design could do wonders. | 3 | 5 | 3
2023-03-10 14:58 | It was really funny and enjoyable | 5 | No It was great maybe except the double jump | 2 | DOuble jump some times | 5 | Maybe the Hit box of the enemies , because you need to be near of them to kill them | 4 | 5 | 5
2023-03-10 15:02 | Good overall, looks promising | 6 | Pretty cool | 2 | The first frame of each movement are weird but its only doing it 1 time | 4 | No, I'm waiting for the full game | 4 | 4 | 4
2023-03-10 15:03 | It was goof | 4 | Great | 3 | Stay block on an enemy, the platforms seems to height and 2 two enemy can be "superposé" and attack you so you can be killed easily | 5 | / | 4 | 3 | 5
2023-03-10 15:03 | A good casual platformer | 8 | No | 3 | Maybe explain clearly than double jump exist | 4 | Give impact to the parry (maybe planned) | 4 | 4 | 3
2023-03-10 15:08 | Good | 7 | Little issue when you arrived in a new level but it just during 1 second | 2 | Little issue when you arrived in a new level | 3 | No it is a good game | 4 | 4 | 4
2023-03-10 15:14 | Fairly good | 6 | No there wasn't any problem, the keys where quite fast responsive | 3 | When you are jumping on an enemy, he doesn't die. | 4 | The game doesn't have a history, but the game is nice and very good | 4 | 1 | 4
2023-03-10 15:18 | Really good for a demo | 8 | good | 2 | We can go outside of the map on the last level by jumping over the wall | 4 | Be carefull with the double jump | 4 | 4 | 4
2023-03-10 15:32 | What is your overall impression of the game ? | 6 | How responsive were the game controls? Were there any issues with latency or delay? | 3 | Were there any bugs, glitches, or technical issues that you encountered while playing? | 3 | Is there anything else you'd like to share about your experience playing the game? | 3 | 3 | 3
2023-03-10 15:40 | Very Good | 7 | fine, | 2 | yes at the end we can go out of the wall | 4 | no | 4 | 3 | 4
2023-03-10 15:46 | It has a good potential for a ninja gaiden like. | 4 | The game controls is responsive. | 3 | Don't see any bug so far. | 3 | No thanks. | 3 | 3 | 2
2023-03-10 15:48 | The project seems to be on a good way | 6 | Maybe on the "double jump", sometimes, I could jump high, sometimes not | 1 | I felt... is it... normal ? 🤔 | 3 | No | 4 | 3 | 3

## Result Test Session 10032023.
| What is your overall impression of the game ? | How would you rate the game's graphics and visual effects? | How responsive were the game controls? Were there any issues with latency or delay? | How difficult was the game? Did you find it too easy, too difficult, or just right? | Were there any bugs, glitches, or technical issues that you encountered while playing? | Would you recommend this game to others? | Is there anything else you'd like to share about your experience playing the game? | How would you rate the game's controls ? | Do you like that we can be kill by one hit ? | Do you fin the game fluid and smooth ?
2023-03-10 14:53 | Good. Very promising, needs a level design concept, but its a pretty polished prototype. | 8 | Quite responsive. The double jump is well done, but the movement feels sluggish at times. | 2 | Nothing beyond the obvious. | 3 | Looking forward to seeing a more evolved version. A bit of extra works on the mechanics and more interesting levele design could do wonders. | 3 | 5 | 3
2023-03-10 14:58 | It was really funny and enjoyable | 5 | No It was great maybe except the double jump | 2 | DOuble jump some times | 5 | Maybe the Hit box of the enemies , because you need to be near of them to kill them | 4 | 5 | 5
2023-03-10 15:02 | Good overall, looks promising | 6 | Pretty cool | 2 | The first frame of each movement are weird but its only doing it 1 time | 4 | No, I'm waiting for the full game | 4 | 4 | 4
2023-03-10 15:03 | It was goof | 4 | Great | 3 | Stay block on an enemy, the platforms seems to height and 2 two enemy can be "superposé" and attack you so you can be killed easily | 5 | / | 4 | 3 | 5
2023-03-10 15:03 | A good casual platformer | 8 | No | 3 | Maybe explain clearly than double jump exist | 4 | Give impact to the parry (maybe planned) | 4 | 4 | 3
2023-03-10 15:08 | Good | 7 | Little issue when you arrived in a new level but it just during 1 second | 2 | Little issue when you arrived in a new level | 3 | No it is a good game | 4 | 4 | 4
2023-03-10 15:14 | Fairly good | 6 | No there wasn't any problem, the keys where quite fast responsive | 3 | When you are jumping on an enemy, he doesn't die. | 4 | The game doesn't have a history, but the game is nice and very good | 4 | 1 | 4
2023-03-10 15:18 | Really good for a demo | 8 | good | 2 | We can go outside of the map on the last level by jumping over the wall | 4 | Be carefull with the double jump | 4 | 4 | 4
2023-03-10 15:32 | What is your overall impression of the game ? | 6 | How responsive were the game controls? Were there any issues with latency or delay? | 3 | Were there any bugs, glitches, or technical issues that you encountered while playing? | 3 | Is there anything else you'd like to share about your experience playing the game? | 3 | 3 | 3
2023-03-10 15:40 | Very Good | 7 | fine, | 2 | yes at the end we can go out of the wall | 4 | no | 4 | 3 | 4
2023-03-10 15:46 | It has a good potential for a ninja gaiden like. | 4 | The game controls is responsive. | 3 | Don't see any bug so far. | 3 | No thanks. | 3 | 3 | 2
2023-03-10 15:48 | The project seems to be on a good way | 6 | Maybe on the "double jump", sometimes, I could jump high, sometimes not | 1 | I felt... is it... normal ? 🤔 | 3 | No | 4 | 3 | 3